## Sheet1
Tasks | Start Date | Who's Responsible | Staus
Six Months Prior
Develop compelling case for campaign for Partners | 2016-03-01 | Membership Dir./ ED/ Sustainability Committee | Complete
Establish Campaign Goals | 2016-03-15 | ED/Membership Dir. /Board | Complete
Five Months Prior
Partnership Campaign Info Sessions 4/7 9:00 AM, 4/13 12:00 PM, 4/20 8:30 AM | 2016-04-01 | Membership Dir/ Sustainability Committee | Complete
Develop Job Descriotions - Chairs & Leads | 2016-04-15 | Membership Dir. | Complete
Four Months Prior
Recruit Campaign Chairs | 2016-05-01 | Membership Dir/ Sustainability Committee | Complete
Recruit Campaign Leads | 2016-05-01 | Membership Dir. | Complete
Draft Case for Support | 2016-05-01 | Membership Dir/ED/Communications Dir | Complete
Three Months Prior
Begin Developing a prospect list | 2016-06-01 | Membership Dir./ Campaign Committee | Ongoing
Name Campaign | 2016-06-01 | ED/ Membership Dir. Campaign Chairs | Complete
Develop campaign events and dates and times - Do what we do, Jeffersonian , Story Telling | 2016-06-01 | Membership Dir./ Sustainability Committee | Ongoing
Begin meeting with long-term Prospects | 2016-06-01 | ED/ Membership Dir. Campaign Chairs
Develop campaign materials | 2016-06-01 | Membership Dir./ Communications Dir./ Campaign Chairs | In-process
Two Months Prior
Establish campaign meeting dates and times | 2016-07-01 | Membership Dir./ Campaign Chairs
One Month Prior
Campaign Materials on Connect/Website | 2016-08-15
Prospect List on Connect | 2016-08-30
Hold campaign trainings | 2016-08-01 | Membership Dir./ ED/ Campaign Chairs | Complete
Campaign Kick-Off
Fall Social/Campaign Kickoff | 2016-09-15 | SVP Staff, Host Mary Schweitzer | Confirmed
Do What We Do | 2016-09-28 | SVP Staff, Host Randi Grassgreen at Crestone | Confirmed
Jeffersonian Dinner - Topic Attention Homes | 2016-10-09 | Jeanette Marquess, Host Ed Victor | Host Confirmed, Attention Homes Confirmed
Jeffersonian Dinner - WOW! | TBD - Oct | Jeanette Marquess, Host Stephanie Wilson | Host Confirmed, WOW! confirmed
Jeffersonian Dinner - Bridge House | 2016-10-13 | Jeanette Marquess, Host Jon Hinebauch, John McCorvie & Bridge House | Host and Bridge House confirmed
Jeffersonian Dinner - Execs Evolve | 2016-10-05 | Jeaneatte Marquess, Host Betsy Homes and Jeremy Yazinski | Confirmed, Invite 2 Program Particpants to attend
Story Telling Event | TBD - Nov | Ali Kegley
Advertising
Boulder Lifestyle Mag | 2016-08-01 | paid ad #1, Around Town announcement, Lifestyle Calendar entry | Appear September
Boulder Lifestyle Mag | 2016-09-01 | paid ad #2, Lifestyle Calendar entry | Appear October
Boulder Lifestyle Mag | 2016-10-01 | Good Times photos, Lifestyle Calendar entry | Appear November
Boulder Daily Camera - Eleven full-color 3” x 10” ads, appearing 2x/w in Sunday Local (DC’s highest circulation day) and Monday Business Plus (extended section) |  |  | 8/28 & 8/29, 9/4&9/5, 9/18&9/19, 9/25&9/26, 10/30&10/31, 10/6
Campaign Checklist