## Sheet1
SVP Outreach Work Plan 2016-17
ITEM | WHO IS RESPONSIBLE | WHO ELSE IS INVOLVED AND HOW | TIMING | NOTES/QUESTIONS | Status
Prospective Partner Events | Lead: Andy |  |  | Goal: 10 evening and 4 lunch. Alternate Seattle/Eastside
Review/update as necessary job descriptions for MC, Host, Steward, Notetaker | Andy | Rebecca |  | MCs and Stewards must be on outreach committee or staff. Steward can ask another partner to be notetaker. We are combining MC and Steward for now.
Generate list of potential partners for hosts, attending, etc. | Andy/Rebecca | Committee
Identify Hosts, MCs, partners, Eds, Stewards | Andy |  | Ongoing | Have host decide on day that works best for them. Should be MTWT. Schedule 3-4 months in advance Use this as a way to engage many partners
Arrange catering, wine, tags, video | Juliet | Coordinate with Andy | Ongoing
Post online and newsletter | Willow |  | Ongoing
Marketing/Messaging | Lead:
Review and update script | Janet / Rebecca | Committee | September
Review web site info
Review prospect folder info | LisaN/Willow |  | done
Analysis | Lead: |  |  | Goal: identify best use of resources
Review prospect to partner pipeline | Andy | Rebecca and Janet | September | Key questions: Number of new partners who attended PPR vs other ways What did it take for people to join? Just PPR? PPR and meeting? Just meeting? Amount of time it took Attendance at PPRs by month
Prospect Follow Up | Lead: Andy |  |  | Goal: Ensure timely and ongoing followup and steweardship
Review/Refresh steward emails | Janet | Committee input | September | Need one for prospects who attended the event, one for no-shows, then for six weeks after event, six months after the event, and 18 months after the event.
Review processs, reminders, etc. | Committee |  | September | Review and refresh at September meeting
Gather prospect info | Notetaker, MC, Host, Steward. Partners |  | ongoing | After event, Notetaker writes up notes and sends to other partners who attended the event to add to the notes.
Enter Prospects into SalesForce | Staff |  | ongoing | Above info is sent to staff to enter into SalesForce
Follow up | Steward for Event |  | immediately after event and then ongoing | Steward sends sample email to all who attended and all no shows, continues to follow up using suggested time frame. BCC Andy and/or send him an email telling him when to remind you.
Reminders | Staff and Stewards |  | Monthly | Beginning of each month, Staff creates report from SalesForce on who needs reminders during that month. The list is given to each Steward. Stewards do appropriate follow up emails.
One-on-ones for prospects who do not attend events | Staff and CoChairs |  | ongoing | If we have prospects who want to meet with someone instead of or in addition to coming to a prospective partner event, arrangements will be made. Should always try to have a partner join this meeting Steward will be determined on ad hoc basis
Former partners | Janet/Staff |  | Monthly | Staff will follow up with former partners. When a partner leaves, a reminder will be set for 9 months.
Review | Outreach Team |  | Monthly | Part of each monthly meeting will be to talk about what is or is not working and how to proceed.
U35 | n/a |  |  | Move to discussion about Diversity.
Reporting | Lead: Andy |  |  | Goal: Track where we are
Standard | Staff |  | Monthly | Monthly report should include: who cancelled, who joined with info about who referred each prospect and Steward for that prospect and if U35.
New partners | Staff |  | Monthly | Outreach committee will be sent the full text filled out when partners join.
Extra | Staff |  | TBD | As we get into the new process, we can identify what additional reporting is necessary.
Fast Pitch | Lead: |  |  | Goal: Recruitment before, at, and after the event -- volunteers and attendees
Identify where in FP program to "market" SVP
How to follow up with volunteers
How to follow up with attendees
Ambassador Program | Lead: Brooke |  |  | Goal: Have all partners be Ambassadors. Encourage all partners to recruit new partners. Must make it easy for them.
Partner Meetings | Committee | staff advise |  | we should promote the program at every partner meeting in multiple ways
Other committee meetings | Committee |  |  | present briefly at NGC, PGC, CATs, etc.
Recognition of partners who recruit | Committee | Staff | ongoing | recognize at Partner Meetings, in newsletter other public ways, thank you from staff/ED when they refer someone
Ambassador Tools | Committee | Staff | yearly
Linked IN
Diversity Strategy | Leads: Susan and Sharon |  |  | Goal: Develop and pilot a strategy that will ultimately lead to a more diverse partnership; understand why diverse partners do/do not join
U35
Corporate Partners | Lead: Lisa Merrill |  |  | Goal: Develop corporate partnerships
Moving to a different group