| 2015-2016 COMMUNICATIONS WORKPLAN (REVISED FEBRUARY 26, 2016) |
| --- |
| Organizational Priorities: Successful ED Integration ¦ Thriving Staff ¦ Get On Message and Get It Out ¦ Clear Roles & Decision-Making ¦ Revenue & Stability |
| Priorities | Program Goals | % | Key Activities (Those Directly Connected to Org Priorities are Color-Coded) | J | A | S | O | N | D | J | F | M | A | M | J |
| Revenue & Stability Get On Message & Get It Out | Effectively demonstrate our impact, inspiring our audiences to join, renew, donate and engage | 40% | Produce a new impact report (short and long version, both print and online) + new recruiting materials (e.g. new folder, inserts, short impact report, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Update out web-based Investee Portfolio and produce a short print version |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop messaging, materials, and trainings to support fundraising and recruitment |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Write or commission 4-6 stories that demonstrate our unique impact |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Produce or commission 4-6 videos that demonstrate our unique impact |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Provide messaging, story development, design and other support for big events |  |  |  |  |  |  |  |  |  |  |  |  |
| Revenue & Stability | Provide a consistent and valuable stream of information that encourages our audiences to engage with SVP | 20% | Work with program staff to align communications with program needs and create systems to streamline event and volunteer opportunity promotion |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop/collect content for and distribute/promote newsletter, stories, and blog posts |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Keep calendar and volunteer ops current and distribute regular updates to Partners |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Work with Lindsey Engh to tailor social media content (till 3/1) then create in-house |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Support Fast Pitch communications and work with volunteers to keep website current |  |  |  |  |  |  |  |  |  |  |  |  |
| Get On Message & Get It Out | Cultivate strong messengers who can effectively recruit/engage Partners and advocate for our POV in the sector | 7% | Develop messaging frameworks for Collective Action and equity and work with staff to create clear talking points for all our program areas and to identify related stories |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Host workshops to help staff, Board, Outreach Team, and key Partners talk about SVP, our program work, and equity in a clear, consistent, and authentic voice |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Work with Mike, Sally, and new ED to clarify our goals for maintaining SVP’s voice in the sector, identify audiences we want to reach, and line up speaking and writing ops |  |  |  |  |  |  |  |  |  |  |  |  |
| Thriving Staff | Communicate and live values to improve work and solidify brand | 3% | Work with staff and Board to finalize values and incorporate into our communications |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Work with staff to incorporate values into materials, presentations, and conversations |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Encourage ongoing conversations and ops to share stories re: brand and values |  |  |  |  |  |  |  |  |  |  |  |  |
| Successful ED Integration | Integrate and elevate new ED voice in SVP communications | 5% | Introduce ED to our approach to communications, our message framework, etc. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop an editorial calendar to support transition and publish regular pieces from and about our new ED in our newsletter and on our blog |  |  |  |  |  |  |  |  |  |  |  |  |
| Various | Support staff and Partners | 30% | Keep up with general email, attend staff meetings, professional development, etc. + accommodate unplanned opportunities and unexpected tasks |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Build a shared communications team for SVP Seattle and the Network Office |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Help with staff-wide planning + opportunities for clarifying and focusing work |  |  |  |  |  |  |  |  |  |  |  |  |

| COMMUNICATIONS WORKPLAN: PRIORITIES GOALS AND MILESTONES (REVISED FEBRUARY 26, 2016) |
| --- |
| Priorities | Program Goals | Q1 Milestones (Jul-Sept) | Q2 Milestones (Oct-Dec) | Q3 Milestones (Jan-Mar) | Q4 Milestones (Apr-Jun) |
| Successful ED Integration: SVP’s new Executive Director is set up for success in his/her leadership role and is integrated into the organizational culture and values. Thriving Staff: SVP staff are able to focus on their work, prioritize their needs, take risks and grow, balance ambition with a reasonable workload, and have a healthy amount of autonomy in their program areas. Get On Message and Get It Out: Staff, Board, and key Partners speak clearly, confidently, and consistently about SVP, particularly in relation to our values, Collective Action, and the integration of equity throughout our work. Clear Roles & Decision-Making: Staff and Board members are clear on who is making what decisions, when, and how. Revenue & Stability: Everyone sees their role in retention, recruitment, and/or fundraising and key roles are filled during the ED transition and Rebecca’s maternity leave. | Effectively demonstrate our impact, inspiring our audiences to join, renew, donate and engage | Fund development materials and trainings complete One written impact story | One written impact story Shared communications team model built and hiring process has begun | One written impact story Five impact videos Shared communications team members are hired, workplans are in place and we’re ready to roll | Impact Report + new recruiting materials Investee Portfolio One written impact story Spring meeting includes compelling messages, stories, and visuals |
|  | Provide a consistent and valuable stream of information that encourages our audiences to engage with SVP | One newsletter (August) At least 2 events updates | One newsletter (did not complete) At least 3 events updates | Two newsletters (January and March) At least 3 events updates | One newsletter (May) At least 3 events updates Communications aligned with program needs and better systems in place |
|  | Cultivate strong messengers who can effectively recruit and engage Partners and advocate for our POV in the sector |  | Collective Action message framework is complete and rolled out to the board |  | Clarity on voice goals and work is underway Planning for messaging workshops for staff, board and key Partners has begun |
|  | Communicate and live values to improve our work and solidify our brand |  | Values are finalized and a plan for incorporation is underway | One staff conversation on brand and values (led by fellow staff members) | One staff conversation on brand and values (led by fellow staff members) |
|  | Integrate and elevate new ED voice in SVP communications |  | New ED is familiar with our message framework and communications Editorial plan in place to introduce new ED | At least one piece by or about new ED | At least one piece by or about new ED |
|  | Support fellow staff and Partners | Help with staff-wide planning, keep up with general email, attend staff meetings, professional development, accommodate unplanned opportunities and unexpected tasks, etc. |